## PS - G433
G-433
Anirudh | 245323733033
Hari | 245323733031
Charan | 245323733010
Aisiri | 245323733002
Neha | 245323733023
Akhil | 245323733011

## Tasks
Task ID | Task Description | Tech Stack | Estimated Completion Date | Actual Completion Date | Challenges Faced
T1 | Understanding Project Problem Statement and Research Paper. | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None
T2 | Setting up Environment: Gmail, Git, LLMs for learning | GIT | ‎4/‎10/‎2025 | ‎4/‎10/‎2025 | None
T3 | Preparing Project Schedule document with respective tasks and estimation | - | ‎4/‎11/‎2025 | ‎4/‎11/‎2025 | None
T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None
T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | ‎4/‎15/‎2025 | 2025-04-15 | None
T6 | Preparing Datasets and getting familiar | Python, MySQL, Excel | 2025-04-16 | 2025-04-18 | Since relevant datasets are not available over internet, we have prepared our own datasets.
T7 | Starting Code using a Pre-trained LLM | Python, Pandas, PyTorch and Transformers | 2025-04-21 |  | Resource limitation running an LLM locally takes a lot of time.
T8 | Preparing a Literature Survey | - | - | - | None
T9
T10
T11
T12
T13
T14
T15
T16
T17
T18
T19
T20
T21
T22
T23
T24
T25

## Anirudh
Anirudh |  | 245323733033
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T3 | Preparing Project Schedule document with respective tasks and estimation | - | - | ‎4/‎11/‎2025 | ‎4/‎11/‎2025 | None | Charan, Hari | - | Divide tasks into pairs of two and work simultaneously
3 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Charan, Hari, Aisiri | -
4 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | -
5 | T6 | Preparing Datasets and getting familiar | Python, MySQL, Excel | Akhil, Charan | 2025-04-16 | 2025-04-18 | Since relevant datasets are not available over internet, we have prepared our own datasets. | Charan, Akhil

## Hari
Hari |  | 245323733031
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Charan, Hari, Aisiri | -
3 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | -

## Charan
Charan |  | 245323733010
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T2 | Setting up Environment: Gmail, Git, LLMs for learning | GIT | - | ‎4/‎10/‎2025 | ‎4/‎10/‎2025 | None | Anirudh, Hari, Aisiri
3 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Anirudh, Hari, Aisiri | -
4 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | -
5 | T6 | Preparing Datasets and getting familiar | Python, MySQL, Excel | - | 2025-04-16 | 2025-04-18 | Since relevant datasets are not available over internet, we have prepared our own datasets. | Charan, Anirudh

## Aisiri
Aisiri |  | 245323733002
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Charan, Hari, Aisiri | -
3 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | -
4 | T8 | Preparing a Literature Survey | - | - | - | - | None | Aisiri

## Neha
Neha |  | 245323733023
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Charan, Hari, Aisiri | - | -
3 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | - | -
4 | T8 | Preparing a Literature Survey | - | - | - | - | None | Aisiri | -

## Akhil
Akhil |  | 245323733011
SI. NO | Task ID | Task Description | Tech Stack | Forwarded by | Estimated Completion Date | Actual Completion Date | Challenges Faced | Order Of Point Of Contact | Brainstorming | Mentor Advices | Team Review
1 | T1 | Understanding Project Problem Statement and Research Paper. | - | - | ‎4‎/‎9/‎2025 | ‎4‎/‎9‎/‎2025 | None | - | - | Understand the Paper and look for online references of the problem
2 | T4 | Revising Pandas and PyTorch Frameworks | Python, Pandas and PyTorch | - | ‎4/‎12/‎2025 | ‎4/‎14/‎2025 | None | Anirudh, Charan, Hari. | -
3 | T5 | Understanding and Learning Transformers according to the given problem statement | Python and Pytorch | - | ‎4/‎15/‎2025 | 2025-04-15 | None | - | -
4 | T6 | Preparing Datasets and getting familiar | Python, MySQL, Excel | - | 2025-04-16 | 2025-04-18 | Since relevant datasets are not available over internet, we have prepared our own datasets. | Charan, Anirudh | -